## Sheet1
Sprint Goal | Sprint # | Story | Story type | Day 1 | Day 2 | Day 3 | Day 4
Setup the basic framework so we can begin coding the various user stories we decided to do for sprint 1 | 1 | As a user I would like the app to have a user tab so I can see/edit personal info such as age, height, etc… | F | 1
| 1 | As a user I would like the app to allow me to customize the main window to display information I think is most important for me so that it's right there when I open the app | F | 4
| 1 | As a user I would like to set walking/running distance goals to help motivate | F | 1
| 1 | As a user I would like to record the amount of calories I eat in a day so I don't overeat | F | 2
| 1 | As a user I would like the app to keep track and display the amount of weight I have lost/gained in the last 7, 30, and 60 days as well as all time to help visualize my progress | F | 4
| 1 | As a user I would like to be able to set a weight goal and have that goal visible on that graph because setting goals is important | F | 2
| 1 | As a user I would a line graph that shows my weight over the past 7, 30, 90 days so I have a visual representation of my weight change | F | 8