## Sheet1
Sprint Goal | Sprint # | Story | Tasks | Story type | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
Line Graph for Weight Tracker | 4 | As a user I would like to be able to set a weight goal and have that goal visible on that graph because setting goals is important | Create a horizontal line on Graph | F | 0 | 0 | 0 | 0 | 0 | 0
| 4 | As a user I would like a line graph that shows my weight over the past 7, 30, 90 days so I have a visual representation of my weight change. | Design a class to display information as a line graph | F | 0 | 0 | 1 | 1 | 0 | 1
Walk/Run Tracker | 4 | As a user I would like the app to track the amount of distance I walk/run | Cellect data from phones pedometer | F | 1 | 1 | 1 | 0 | 0 | 0
|  |  | Display Steps on Screen | F | 0 | 0 | 0 | 0 | 1 | 1
Clean up UI for presentation | 4 | N/A | Make Visual improvements | NF | 0 | 0 | 0 | 0 | 1 | 1