## Sheet1
Sprint Goal | Sprint # | Story | Tasks | Story type | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
Line Graph for Weight Tracker | 6 | As a user I would like to be able to set a weight goal and have that goal visible on that graph because setting goals is important | Create a horizontal line on Graph | F | 2 | 0 | 0 | 0 | 0 | 0
Conduct Usability Study | 6 | N/A | 1. Put the latest build of BlurBodyBalance on an Android phone for participants to use. | N/A | 0 | 0 | 1 | 0 | 0 | 0
|  |  | 2. Create Usability Study Permission Form |  | 0 | 0 | 0 | 1 | 0 | 0
|  |  | 3. Create Usability Study Script |  | 0 | 0 | 0 | 1 | 0 | 0
|  |  | 4. Conduct Study |  | 0 | 0 | 0 | 0 | 1 | 0
Create Message database and deliverer | 6 | As a user I would like the app to be able make notifications to compliment me on completing my goals/ good activity level in order to motivate me. | Create encouraging messages and a delivery for them | F | 0 | 0 | 0 | 0 | 1 | 1