## Sheet1
ID | Story | Sprint | Story priority | Story Status | Story Points | Key
3 | As a user I would a line graph that shows my weight over the past 7, 30, 90 days so I have a visual representation of my weight change | 1 | H | W | 8 | PH - Placeholder
7 | As a user I would like to be able to set a weight goal and have that goal visible on that graph because setting goals is important | 1 | H | W | 2
4 | As a user I would like the app to create smaller goals, or milestones, based on the goal I have set so it helps keep me motivated | PH | M | W | PH
8 | As a user I would like the app to create smaller goals, or milestones, based on the goal I have set so it helps keep me motivated | PH | M | W | PH
12 | As a user I would like the app to keep track and display the amount of weight I have lost/gained in the last 7, 30, and 60 days as well as all time to help visualize my progress | 1 | H | W | 4
9 | As a user I would like to record the amount of calories I eat in a day so I don't overeat | 1 | H | W | 2
15 | As a user I would like to keep track of other nutrition related data (sugar, carbs, fat, etc.) in a similar way to calories | PH | M | W | PH
11 | As a user I would like to keep track of my daily water intake to make sure I stay hydrated | PH | M | W | PH
10 | As a user I would like the app to track the amount of distance I walk/run so I can see if I'm hitting my goals | PH | M | W | PH
2 | As a user I would like to set walking/running distance goals to help motivate | 1 | H | W | 1
1 | As a user I would like to look at pre-existing workout routines for users who don't know/don't have their own workout routines | PH | L | W | PH
5 | As a user I would like the app to try and give an estimated calories burned based on my workouts | PH | M | W | PH
6 | As a user I would like the app to allow me to customize the main window to display information I think is most important for me so that it's right there when I open the app | 1 | H | W | 4
13 | As a user I would like the app to have tabs for weight, diet, and fitness to displays more details than in the main window. | PH | M | W | PH
14 | As a user I would like the app to have a user tab so I can see/edit personal info such as age, height, etc… | 1 | H | W | 1
22 | As a user I would like the app to display a summary page after each day so I can see data for that day and my progress toward my goals | PH | M | W | PH
26 | As a user I would like the app to have a dark theme because I don't want to burn my eyes | PH | H | W | PH
24 | As a user I would like the app to be accessible on multiple platforms for my convenience | PH | H | W | PH
30 | As a user I would like the app to be able to set personal goals to help motivate | PH | M | W | PH
33 | As a user I would like the app to generate a printable report to share with doctor/dietician, or to keep personal record | PH | L | W | PH
35 | As a user I would like the app to allow me to compare/compete with friends I add on the app in order to motivate me | PH | L | W | PH
42 | As a user I would like the app to have leaderboards for different health aspects so I can compete with my friends | PH | L | W | PH